## Instructions
Bid leveling template for subcontractor bids
One trade package per file. Three bidders are set up; copy a four-column bidder block to add more.
How to use it
1 | Build the scope before bids arrive. On "Bid tab", list every CSI MasterFormat section in the trade package (columns A to E): division, section number, scope item, unit and your estimated quantity.
2 | List the inclusions and exclusions you care about on "Scope sheet" and send the same list to every bidder with the invitation to bid.
3 | Enter each bid. For every row: the bidder's unit price (or lump sum with quantity 1), Y or N for whether the scope is included, and a note with the proposal page.
4 | Read the qualifications and cover letter. Any "by others", "excluded" or silent scope gets N. The extended amount for an N row stays blank on purpose.
5 | Check the plugs. Every N row is plugged at the median of the bidders who included it (row "Plugs for excluded scope"). Replace with your own estimate where the median is not credible.
6 | Review the variance columns. Lines far above or below the median are either errors, scope differences or unbalanced pricing. Ask the bidder before you award.
7 | Complete "Award memo": recommended bidder, leveled total, adjustments, open clarifications and who approved. The award decision stays with your team.
Cell colors: white cells are inputs, grey cells are formulas. No macros.
Sample rows on "Bid tab" are illustrative (a Division 09 interiors package). Delete them before you use the file on a live bid.
Bid leveling template by BAU AI (bauai.co/resources/bid-leveling/bid-leveling-template). Free to use and adapt. Sample rows are illustrative, not real bids.

## Bid tab
Bid tab: [Project name], [Trade package]
Sample rows 6 to 13 are illustrative. Enter Y or N in "Incl.". Extended, median, variance and totals are formulas.
Scope (your estimate) |  |  |  |  | Bidder A |  |  |  | Bidder B |  |  |  | Bidder C |  |  |  | Comparison
CSI division | Section | Scope item | Unit | Quantity | Unit price | Extended | Incl. Y/N | Note (proposal page) | Unit price | Extended | Incl. Y/N | Note (proposal page) | Unit price | Extended | Incl. Y/N | Note (proposal page) | Median extended | Variance A | Variance B | Variance C
09 | 09 21 16 | Gypsum board assemblies, walls | SF | 42000 | 20 |  | Y |  | 20.7 |  | Y |  | 26.75 |  | Y | Level 5 finish carried throughout
09 | 09 22 16 | Non-structural metal framing | SF | 42000 | 9.8 |  | Y |  | 9.5 |  | Y |  | 10.1 |  | Y
09 | 09 51 13 | Acoustical panel ceilings | SF | 18500 | 9.95 |  | Y |  | 10.4 |  | Y |  |  |  | N | Excluded, qualification 4
09 | 09 65 13 | Resilient base | LF | 6200 | 9.05 |  | Y |  | 7.75 |  | Y |  | 11.5 |  | Y
09 | 09 67 23 | Resinous flooring, loading dock | SF | 3400 |  |  | N | Not mentioned in proposal | 27.2 |  | Y |  | 30.6 |  | Y
09 | 09 91 23 | Interior painting | SF | 96000 | 2.9 |  | Y |  | 2.95 |  | Y |  | 3.05 |  | Y
07 | 07 84 00 | Firestopping at rated walls | LS | 1 | 18500 |  | Y |  |  |  | N | By others per cover letter | 22000 |  | Y
01 | 01 74 00 | Final cleaning, trade areas | LS | 1 | 6500 |  | Y |  | 5800 |  | Y |  |  |  | N | Excluded
Base total (included scope only)
Plugs for excluded scope (median of bidders who included it)
Leveled total
Rows marked N (count)
Bid leveling template by BAU AI (bauai.co/resources/bid-leveling/bid-leveling-template). Free to use and adapt. Sample rows are illustrative, not real bids.

## Scope sheet
Scope sheet: inclusions and exclusions checklist
Send this list with the invitation to bid. Mark each bidder Y (included), N (excluded) or ? (unclear, ask). Unclear items go on the scope review call.
Item | Bidder A | Bidder B | Bidder C | Clarification needed / proposal page
All addenda acknowledged (list numbers in note)
Bid form complete, alternates priced
Unit prices provided where the bid form asks
Bid bond provided (if required)
Performance and payment bonds included (if required)
Insurance per subcontract requirements
Sales tax included
Prevailing wage rates carried (if the project requires them)
Permits and inspection fees for this trade
Layout from GC control lines
Hoisting, lifts and equipment
Material storage and protection
Daily cleanup and debris removal
Final cleaning of trade areas
Firestopping and penetration sealing for this trade
Patching after other trades
Temporary protection of finished work
Mock-ups and samples
Submittals, shop drawings and closeout documents
Warranty per specifications
Overtime or shift work if the schedule requires it
Exclusions listed in the cover letter reviewed
Count of N or ?
Bid leveling template by BAU AI (bauai.co/resources/bid-leveling/bid-leveling-template). Free to use and adapt. Sample rows are illustrative, not real bids.

## Award memo
Award memo
One page per trade package. The award decision stays with your team.
Project
Trade package
Date
Prepared by
Recommended bidder
Recommended leveled total
Runner-up and why it did not win
Adjustments made (plugs, alternates, allowances)
Open clarifications
Unbalanced or outlier lines reviewed
Risks carried
Approved by
Leveled totals from "Bid tab"
Lowest leveled total
Bid leveling template by BAU AI (bauai.co/resources/bid-leveling/bid-leveling-template). Free to use and adapt. Sample rows are illustrative, not real bids.